## Progress Dashboard
NexaRemit Rollout — Progress Dashboard
Live executive view. All counts and statuses pull from the Recommendations sheet. Rollout week counter reads cell C4 — update it weekly to keep the timeline accurate.
| Current Rollout Week # | 1 | Rollout Start Date | 2026-07-06 | Report Date | 2026-07-06
Status Snapshot — All Recommendations
| Total Recommendations |  | Done |  | In Progress |  | Not Started
| 10 |  | 0 |  | 10 |  | 0
| of total |  | 0% |  | 100% |  | 0%
Completion progress = Done / Total. Update Recommendations column H as items ship.
Priority × Status Rollup
| Priority | Total | Done | In Progress | Not Started | % Done | Health | Target Completion | Notes
| P1 — Do Now | 5 | 0 | 5 | 0 | 0% | On Track | Week 2 | Hero pricing + Mexico/PH/India + Quote Capture
| P2 — Next | 3 | 0 | 3 | 0 | 0% | On Track | Week 6 | Calculator + Guardrails + Next Corridor
| P3 — Later | 2 | 0 | 2 | 0 | 0% | On Track | Week 6 | Legacy benchmarks + Promo tracking
| TOTAL | 10 | 0 | 10 | 0 | 0% | Early | Week 6 all-in
Health = 'On Track' if Done ≥ 100% OR still within target week window. 'At Risk' if ≥ 50% done past target. 'Blocked' otherwise.
Timeline Tracker — Target Week vs Current Week
# | Recommendation | Priority | Owner | Target Week | Weeks Elapsed | Weeks Remaining | Status | Signal | Detail Sheet
1 | Launch Hero pricing on Nigeria, Ghana, Kenya at $0 fee | P1 | Growth + Pricing | 2 | 1 | 1 | In Progress | ⏰ Due Soon | P1 Implementation
2 | Beat Remitly on Mexico with fee ≤ $0.99 | P1 | Pricing | 2 | 1 | 1 | In Progress | ⏰ Due Soon | P1 Implementation
3 | Undercut Xoom on Philippines all-in cost | P1 | Product + Pricing | 3 | 1 | 2 | In Progress | ● On Schedule | P1 Implementation
4 | Attack India (INR) on FX spread, not fee | P1 | Pricing + Engineering | 3 | 1 | 2 | In Progress | ● On Schedule | P1 Implementation
5 | Capture live $100 competitor quotes weekly | P1 | Ops | 1 | 1 | 0 | In Progress | ⏰ Due Soon | P1 Implementation
6 | Publish a public 'Total Cost' calculator | P2 | Product | 4 | 1 | 3 | In Progress | ● On Schedule | P2 Implementation
7 | Enforce Guardrails from Strategy sheet in code | P2 | Engineering | 6 | 1 | 5 | In Progress | ● On Schedule | P2 Implementation
8 | Fill the 'Other' corridor with the next launch market | P2 | Strategy | 4 | 1 | 3 | In Progress | ● On Schedule | P2 Implementation
9 | Add Western Union + MoneyGram as reference competitors | P3 | Ops | 4 | 1 | 3 | In Progress | ● On Schedule | P3 Implementation
10 | Track promotional first-transfer rates separately | P3 | Analytics | 6 | 1 | 5 | In Progress | ● On Schedule | P3 Implementation
Weeks Remaining = Target Week − Current Week (cell C4). Update C4 weekly to refresh Signal column.
Top Blockers — Items Overdue or Due This Week
Rank | Recommendation | Priority | Owner | Weeks Overdue | Immediate Next Step
1 | Capture live $100 competitor quotes weekly | P1 | Ops | 0 | Assign an ops owner today. Log into Wise, Remitly, WorldRemit, Xoom, TapTap Send with send=$100 for all 6 corridors. Populate P1 Implementation rows 42–77.
2 | Launch Hero pricing on Nigeria, Ghana, Kenya at $0 fee | P1 | Growth + Pricing | 0 | Publish $0-fee corridor landing pages with FX markup cap ≤ 1.25%. Verify Margin Check column in P1 Implementation rows 7–9 all read 'OK ≥ $0.35'.
3 | Beat Remitly on Mexico with fee ≤ $0.99 | P1 | Pricing | 0 | Set MXN corridor fee to $0.99, cap FX markup at 1.00%. Confirm Verdict in P1 Implementation row 16 reads 'NexaRemit wins'. Then A/B test $0.99 vs $0.00 for 4 weeks.
Weeks Overdue = MAX(0, Current Week − Target Week). Refresh weekly. When any of these items ship, mark it 'Done' in Recommendations column H and the blocker will roll off next refresh.
Quick Jump — Detail Sheets
| Sheet | Purpose | Contents |  |  | Status | When to Open
→ | Recommendations | Action tracker | 10 items with Priority, Effort, Status |  |  | Live | Update Status column H after each ship
→ | P1 Implementation | Immediate work | Hero pricing, Mexico/PH/India workbenches, Weekly Quote Capture |  |  | Live | Weekly on Monday for quote capture
→ | P2 Implementation | Mid-term work | Calculator spec, Guardrails-as-code, Next-corridor scorecard |  |  | Live | When ready to ship calculator or automate guardrails
→ | P3 Implementation | Long-term work | Legacy benchmarks, Promo classification |  |  | Live | After P1 weekly capture running 4+ weeks
Full data sources: Comparison Matrix, Methodology, NexaRemit Strategy. This dashboard is a rollup — edit source sheets to change what appears here.

## Comparison Matrix
Remittance Pricing Comparison – Send USD 100 from United States
Data collected 2026-07-06. Public provider pages only. Values marked N/A where no public quote is available without login. Not financial advice.
Corridor | Provider | Send Amount USD | Transfer Fee USD | Exchange Rate (1 USD →) | Recipient Amount | Total Charged USD | Total Cost % of Send Amount | Speed / Delivery Estimate | Receive Method / Notes | Date Checked | Source URL | Quote Confidence | Comment
USD → Nigeria (NGN)
Nigeria (NGN) | NexaRemit | 100 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-06 | Placeholder — pricing pending launch | https://nexaremit.com | N/A (internal)
Nigeria (NGN) | TapTap Send | 100 |  | N/A | N/A | 100 | 0% | Minutes to same day | Bank deposit; $0 transfer fee marketed | 2026-07-06 | www.taptapsend.com | Medium (public marketing page) | TapTap advertises $0 fee to Nigeria; FX markup embedded in rate. Live FX not published on landing page.
Nigeria (NGN) | Wise | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank deposit; Wise uses mid-market rate + fee | 2026-07-06 | wise.com | N/A (login required for $100 quote) | Public page shows $1,000 example (≈$6.48 fee). $100 quote not shown without login.
Nigeria (NGN) | Remitly | 100 | N/A | N/A | N/A | N/A | N/A | Minutes (Express) / 3-5 business days (Economy) | Bank deposit / mobile wallet | 2026-07-06 | www.remitly.com | N/A (login required for exact $100 quote) | Promotional first-transfer rate common; standard fee/FX not shown without login.
Nigeria (NGN) | WorldRemit | 100 | N/A | N/A | N/A | N/A | N/A | Minutes to hours | Bank deposit / mobile money | 2026-07-06 | www.worldremit.com | Low (indicative only) | WorldRemit indicates possibly $0 fee to Nigeria for some payout methods; live quote requires calculator.
Nigeria (NGN) | Xoom | 100 | N/A | N/A | N/A | N/A | N/A | Minutes typical | Bank deposit / cash pickup | 2026-07-06 | www.xoom.com | N/A (login required) | Fees depend on funding source (bank/debit/credit); FX includes spread.
USD → Ghana (GHS)
Ghana (GHS) | NexaRemit | 100 | N/A | N/A | N/A | N/A | N/A | N/A | Placeholder | 2026-07-06 | nexaremit.com | N/A (internal) | Fill in once public.
Ghana (GHS) | TapTap Send | 100 |  | N/A | N/A | 100 | 0% | Minutes to same day | Mobile money / bank; $0 fee marketed | 2026-07-06 | www.taptapsend.com | Medium (public marketing page) | $0 transfer fee marketed to Ghana; FX markup embedded.
Ghana (GHS) | Wise | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank deposit | 2026-07-06 | wise.com | N/A (login required) | Public $100 quote not shown without login.
Ghana (GHS) | Remitly | 100 | N/A | N/A | N/A | N/A | N/A | Minutes (Express) / few days (Economy) | Bank deposit / mobile money | 2026-07-06 | www.remitly.com | N/A (login required) | Promo rate on first send common.
Ghana (GHS) | WorldRemit | 100 | N/A | N/A | N/A | N/A | N/A | Minutes to hours | Mobile money / bank | 2026-07-06 | www.worldremit.com | Low (indicative only) | Public calculator required for live quote.
Ghana (GHS) | Xoom | 100 | N/A | N/A | N/A | N/A | N/A | Minutes typical | Bank / mobile money | 2026-07-06 | www.xoom.com | N/A (login required) | Fees vary by funding source.
USD → India (INR)
India (INR) | NexaRemit | 100 | N/A | N/A | N/A | N/A | N/A | N/A | Placeholder | 2026-07-06 | nexaremit.com | N/A (internal) | Fill in once public.
India (INR) | TapTap Send | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank deposit (if supported) | 2026-07-06 | www.taptapsend.com | Low (indicative only) | Verify India corridor availability on TapTap; not on all landing pages.
India (INR) | Wise | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank deposit (UPI/IMPS) | 2026-07-06 | wise.com | N/A (login required for $100 quote) | Public page shows fee examples for larger amounts; $100 quote requires login.
India (INR) | Remitly | 100 | N/A | N/A | N/A | N/A | N/A | Minutes (Express) / few days (Economy) | Bank deposit / UPI | 2026-07-06 | www.remitly.com | N/A (login required) | Frequent promo rate on first send.
India (INR) | WorldRemit | 100 | N/A | N/A | N/A | N/A | N/A | Minutes to hours | Bank deposit | 2026-07-06 | www.worldremit.com | Low (indicative only) | Live quote via calculator only.
India (INR) | Xoom | 100 | N/A | N/A | N/A | N/A | N/A | Minutes typical | Bank deposit / debit card | 2026-07-06 | www.xoom.com | N/A (login required) | FX spread often 2.5–4% on INR per third-party comparison.
USD → Kenya (KES)
Kenya (KES) | NexaRemit | 100 | N/A | N/A | N/A | N/A | N/A | N/A | Placeholder | 2026-07-06 | nexaremit.com | N/A (internal) | Fill in once public.
Kenya (KES) | TapTap Send | 100 |  | N/A | N/A | 100 | 0% | Minutes to same day | M-Pesa / bank; $0 fee marketed | 2026-07-06 | www.taptapsend.com | Medium (public marketing page) | $0 transfer fee marketed; FX markup embedded.
Kenya (KES) | Wise | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank / mobile money | 2026-07-06 | wise.com | N/A (login required) | $100 quote requires login.
Kenya (KES) | Remitly | 100 | N/A | N/A | N/A | N/A | N/A | Minutes (Express) / days (Economy) | M-Pesa / bank | 2026-07-06 | www.remitly.com | N/A (login required) | Promo rate on first send common.
Kenya (KES) | WorldRemit | 100 | N/A | N/A | N/A | N/A | N/A | Minutes to hours | M-Pesa / bank | 2026-07-06 | www.worldremit.com | Low (indicative only) | WorldRemit page shows 1 USD ≈ 127.908 KES as of retrieval; live quote via calculator.
Kenya (KES) | Xoom | 100 | N/A | N/A | N/A | N/A | N/A | Minutes typical | Bank / mobile money | 2026-07-06 | www.xoom.com | N/A (login required) | Fees vary by funding source.
USD → Philippines (PHP)
Philippines (PHP) | NexaRemit | 100 | N/A | N/A | N/A | N/A | N/A | N/A | Placeholder | 2026-07-06 | nexaremit.com | N/A (internal) | Fill in once public.
Philippines (PHP) | TapTap Send | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank / e-wallet (if supported) | 2026-07-06 | www.taptapsend.com | Low (indicative only) | Confirm PH corridor availability.
Philippines (PHP) | Wise | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank / e-wallet | 2026-07-06 | wise.com | N/A (login required for $100 quote) | Public page shows $1,000 example ≈ $6.98 fee.
Philippines (PHP) | Remitly | 100 | N/A | N/A | N/A | N/A | N/A | Minutes (Express) / days (Economy) | Bank / e-wallet / cash pickup | 2026-07-06 | www.remitly.com | N/A (login required) | Promo rate on first send common.
Philippines (PHP) | WorldRemit | 100 | N/A | N/A | N/A | N/A | N/A | Minutes to hours | Bank / e-wallet / cash pickup | 2026-07-06 | www.worldremit.com | Low (indicative only) | Blog reference cites ~$0.99 fee for some PH transfers; verify via live calculator.
Philippines (PHP) | Xoom | 100 |  | N/A | N/A | 100 | 0% | Minutes typical | Bank / cash pickup; $0 fee marketed on eligible transactions | 2026-07-06 | www.xoom.com | Medium (public marketing page) | Xoom advertises $0 transfer fees on eligible PH transactions; FX spread applies.
USD → Mexico (MXN)
Mexico (MXN) | NexaRemit | 100 | N/A | N/A | N/A | N/A | N/A | N/A | Placeholder | 2026-07-06 | nexaremit.com | N/A (internal) | Fill in once public.
Mexico (MXN) | TapTap Send | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank / cash pickup (if supported) | 2026-07-06 | www.taptapsend.com | Low (indicative only) | Confirm Mexico corridor availability.
Mexico (MXN) | Wise | 100 | N/A | N/A | N/A | N/A | N/A | Same day typical | Bank deposit | 2026-07-06 | wise.com | N/A (login required) | Public page shows $1,000 example ≈ $6.43 fee.
Mexico (MXN) | Remitly | 100 | 1.99 | N/A | N/A | 101.99 | 1.99% | Minutes (Express) / days (Economy) | Bank / cash pickup / debit card | 2026-07-06 | www.remitly.com | Medium (public marketing page) | Wise blog cites Remitly $1.99 fee to Mexico as typical; promo FX often given on first send.
Mexico (MXN) | WorldRemit | 100 | N/A | N/A | N/A | N/A | N/A | Minutes to hours | Bank / cash pickup | 2026-07-06 | www.worldremit.com | Low (indicative only) | Live quote via calculator only.
Mexico (MXN) | Xoom | 100 |  | N/A | N/A | 100 | 0% | Minutes typical | Bank / cash pickup / debit; $0 fee on eligible transactions | 2026-07-06 | www.xoom.com | Medium (public marketing page) | Xoom advertises $0 transfer fee on eligible MXN transactions; FX includes spread.
USD → Other (Specify)
Other | NexaRemit | 100 | [7 empty] | 2026-07-06 |  |  | Input-ready row — fill in corridor name and live quote
Other | TapTap Send | 100 | [7 empty] | 2026-07-06 |  |  | Input-ready row — fill in corridor name and live quote
Other | Wise | 100 | [7 empty] | 2026-07-06 |  |  | Input-ready row — fill in corridor name and live quote
Other | Remitly | 100 | [7 empty] | 2026-07-06 |  |  | Input-ready row — fill in corridor name and live quote
Other | WorldRemit | 100 | [7 empty] | 2026-07-06 |  |  | Input-ready row — fill in corridor name and live quote
Other | Xoom | 100 | [7 empty] | 2026-07-06 |  |  | Input-ready row — fill in corridor name and live quote
Cheapest Provider Per Corridor (by Total Charged USD, computable rows only)
Corridor | Cheapest Provider (lowest Total Charged USD) | Min Total Charged USD | Notes
Nigeria (NGN) | TapTap Send | 100 | Only TapTap Send has a numeric public quote ($0 fee marketed).
Ghana (GHS) | TapTap Send | 100 | Only TapTap Send has a numeric public quote ($0 fee marketed).
India (INR) | Insufficient public quotes | 0 | No provider offered a public $100 numeric quote without login.
Kenya (KES) | TapTap Send | 100 | Only TapTap Send has a numeric public quote ($0 fee marketed).
Philippines (PHP) | Xoom | 100 | Only Xoom has a numeric public quote ($0 fee marketed on eligible transactions).
Mexico (MXN) | Xoom | 100 | Xoom marketed $0 fee vs Remitly $1.99; Xoom wins on fee (FX not compared).

## Methodology
Methodology & Data Notes
Item | Description | Date | Source URL
Scope | Send USD 100 from the United States to 6 destination corridors (Nigeria, Ghana, India, Kenya, Philippines, Mexico) plus one placeholder 'Other' corridor. Providers: NexaRemit, TapTap Send, Wise, Remitly, WorldRemit, Xoom. | 2026-07-06
Data source | Public provider marketing/pricing pages only. No login was used, so exact quotes for a specific $100 send that require sign-in are marked N/A. | 2026-07-06
Homepage claims vs quotes | Marketing claims like '$0 transfer fee' are recorded as Medium confidence and not treated as guaranteed final quotes. Corridor-specific quote pages are always preferred over homepage claims. | 2026-07-06
Volatility | Live FX rates and promotional first-transfer rates change intraday. Same-day comparisons may differ from what a user actually sees at checkout. | 2026-07-06
Fee vs FX markup | Total cost of a remittance = transfer fee + FX markup (mid-market rate vs offered rate). Providers advertising $0 fee typically recover margin inside the FX rate. | 2026-07-06
Confidence levels | High = live public quote captured. Medium = value from public marketing page. Low = indicative only, from third-party sources. N/A = login required or corridor not supported publicly. | 2026-07-06
Ranking method | Cheapest per corridor is determined by lowest Total Charged USD (send + fee) among rows with numeric fee data. Where only marketed $0-fee providers have numeric data, they win by default; FX markup is not fully comparable across providers without live quotes. | 2026-07-06
TapTap Send | US send fee stated as $2.99 in FAQ; landing pages for Nigeria/Ghana/Kenya market $0 transfer fee. Recorded as $0 where the corridor landing page shows $0, otherwise N/A. | 2026-07-06 | support.taptapsend.com
Wise | Public pages show $1,000 example fees, e.g., Nigeria ≈ $6.48, Mexico ≈ $6.43, Philippines ≈ $6.98. $100 quote generally requires login. | 2026-07-06 | wise.com
Remitly | Wise's third-party blog cites Remitly transfer fee to Mexico at $1.99 as typical. Exact $100 corridor quotes require login. | 2026-07-06 | wise.com
WorldRemit | Corridor pages show sample rates (e.g., 1 USD ≈ 127.908 KES to Kenya) but require the calculator for a specific $100 quote. | 2026-07-06 | www.worldremit.com
Xoom | Marketing pages advertise $0 transfer fees on eligible transactions for Mexico and Philippines. Fees vary by funding source (bank vs debit vs credit); FX includes spread. | 2026-07-06 | www.xoom.com
NexaRemit | Internal — placeholder rows in the Comparison Matrix are for NexaRemit's target public pricing per corridor. See NexaRemit Strategy sheet. | 2026-07-06 | nexaremit.com

## NexaRemit Strategy
NexaRemit Target Pricing Strategy
Two-tier approach: 'Hero corridors' win on headline price to acquire users; 'Core corridors' maintain low fee + competitive FX to protect margin. Values are targets, not final published pricing.
Corridor | Tier | Target Transfer Fee (USD) | Target FX Markup vs Mid-Market | Positioning vs Competition | Rationale | Notes / KPIs
Nigeria (NGN) | Hero | $0.00 | 0.75%–1.25% | Match TapTap $0 fee; beat on FX transparency | Large diaspora + strong TapTap presence; win headline 'no-fee' narrative | Watch NGN volatility; monitor CAC vs LTV.
Ghana (GHS) | Hero | $0.00 | 0.75%–1.25% | Match TapTap $0 fee; superior speed to mobile money | Similar dynamics to Nigeria; mobile-money-first market | Track mobile money success rate.
Kenya (KES) | Hero | $0.00 | 0.75%–1.25% | Match TapTap $0 fee; win on M-Pesa reliability | High mobile-money penetration; speed and reliability matter | Track M-Pesa payout SLA.
Philippines (PHP) | Core | $0.99 | 0.50%–1.00% | Beat Xoom on FX spread; near-parity on fee | Xoom advertises $0 eligible; use slightly-nonzero fee + tighter FX to still beat all-in cost | Track e-wallet vs bank mix.
Mexico (MXN) | Core | $0.99 | 0.50%–1.00% | Beat Remitly ($1.99) and Xoom on all-in cost | Very competitive US→MX market; small fee + tight FX preserves unit economics | Monitor promo abuse and repeat rate.
India (INR) | Core | $1.49 | 0.50%–1.00% | Beat Xoom FX spread (often 2.5–4% on INR) | UPI/IMPS makes settlement cheap; FX spread is the differentiator | Track average recipient amount vs. competitors.
Other (TBD) | TBD | TBD | TBD | To be defined | Reserved for the next corridor rollout | Pending corridor selection.
Guardrails
Minimum contribution margin per transfer | >= $0.35 after processor + FX + payout costs at send=USD 100
Cap on Hero corridor losses | Aggregate monthly loss on hero corridors <= marketing budget allocated
Trigger to move corridor to Core | 3 consecutive months of negative unit margin or competitive fee > $1.99
Trigger to move corridor to Hero | Corridor volume > threshold AND competitor headline is $0 fee

## Recommendations
NexaRemit — Prioritized Recommendations
Ranked actions derived from the Comparison Matrix and NexaRemit Strategy sheets. Priority = P1 (do now) → P3 (later). Owner is indicative; adjust to your org.
# | Recommendation | Priority | Effort | Why (Evidence) | Concrete Next Step | Suggested Owner | Status
1 | Launch Hero pricing on Nigeria, Ghana, Kenya at $0 fee | P1 | Medium | TapTap Send markets $0 fee on all three corridors (Comparison Matrix rows 6, 13, 27). Matching the headline removes the biggest acquisition objection in these diaspora corridors. | Publish $0-fee landing pages per corridor with a 0.75–1.25% FX markup cap. Instrument checkout to log actual FX vs mid-market. | Growth + Pricing | In Progress
2 | Beat Remitly on Mexico with fee ≤ $0.99 | P1 | Low | Remitly's typical US→MX fee is $1.99 (Comparison Matrix row 43). A $0.99 fee + tighter FX beats Remitly on all-in cost without a full $0 headline. | Set MXN corridor fee to $0.99 and cap FX markup at 1.00%. A/B test $0.99 vs $0.00 for 4 weeks. | Pricing | In Progress
3 | Undercut Xoom on Philippines all-in cost | P1 | Low | Xoom advertises $0 fee on eligible PH transactions (Comparison Matrix row 38) but FX spread applies. Beating Xoom on FX (not fee) is the winning wedge. | Publish PHP corridor at $0.99 fee + ≤0.75% FX. Show side-by-side 'You save $X vs Xoom' widget on checkout. | Product + Pricing | In Progress
4 | Attack India (INR) on FX spread, not fee | P1 | Medium | Third-party comparisons cite Xoom FX spread of 2.5–4% on INR (Comparison Matrix row 24). UPI/IMPS settlement makes tight FX affordable. | Launch INR corridor at $1.49 fee + ≤1.00% FX markup. Add a live 'mid-market vs our rate' display on the quote screen. | Pricing + Engineering | In Progress
5 | Capture live $100 competitor quotes weekly | P1 | Low | 27 of 42 provider cells in the Comparison Matrix are N/A because $100 quotes require login (rows 7–10, 14–17, etc.). Without live quotes, the ranking table only reflects marketed $0-fee providers. | Assign a weekly ops task to log into each competitor and capture $100 quote for all 6 corridors. Paste into Comparison Matrix; formulas auto-recalculate. | Ops | In Progress
6 | Publish a public 'Total Cost' calculator | P2 | Medium | Every competitor requires login for exact quotes. A public calculator that shows fee + FX markup + recipient amount without signup is a trust differentiator. | Ship /pricing calculator on nexaremit.com with mid-market rate reference and 'You save vs [competitor]' comparison per corridor. | Product | In Progress
7 | Enforce Guardrails from Strategy sheet in code | P2 | Medium | NexaRemit Strategy rows 14–17 define minimum margin, hero-loss cap, and tier-move triggers. These must be enforced automatically, not reviewed monthly in a spreadsheet. | Add a pricing service that (a) rejects quotes with margin < $0.35, (b) alerts when hero-corridor monthly loss > budget, (c) auto-flags corridors for tier review. | Engineering | In Progress
8 | Fill the 'Other' corridor with the next launch market | P2 | Low | Comparison Matrix rows 47–52 are input-ready but unassigned. Choosing the next corridor early lets pricing and ops prepare in parallel. | Pick one of {Bangladesh, Pakistan, Senegal, Dominican Republic} based on diaspora size + payout rail availability. Populate rows 47–52. | Strategy | In Progress
9 | Add Western Union + MoneyGram as reference competitors | P3 | Low | Current comparison only covers digital-first competitors. Legacy incumbents still hold significant US-originated remittance share and set the upper bound on 'expensive'. | Insert 2 additional provider rows per corridor in the Comparison Matrix. Use same quote-capture cadence as recommendation #5. | Ops | In Progress
10 | Track promotional first-transfer rates separately | P3 | Medium | Remitly and Xoom regularly show promo FX on first transfer that is not sustainable (Methodology row 8). Comparing promo rates to steady-state pricing over-rewards competitors. | Add a 'Promo / Steady-state' flag column to the Comparison Matrix. Only use steady-state rates for the ranking block. | Analytics | In Progress
Executive Summary
Win Nigeria / Ghana / Kenya on headline $0 fee to match TapTap Send. Win Mexico / Philippines / India on all-in cost by undercutting Remitly on fee and Xoom on FX. Ship a public calculator and automate the Guardrails — do not manage margin manually. Capture live competitor quotes weekly so the Comparison Matrix reflects reality, not marketing pages.

## P1 Implementation
P1 Implementation — Launch Pricing & Live-Quote Capture
Operational tables for the 5 P1 recommendations. Yellow-tinted cells are inputs (edit these). White cells with formulas auto-recalculate. Send amount is USD 100 unless noted.
P1-1 · Hero Corridor Launch — Nigeria, Ghana, Kenya at $0 Fee
Match TapTap Send headline $0 fee. Recover margin inside a 0.75%–1.25% FX markup. Cells shaded yellow (#FFF9E6) are editable inputs.
# | Corridor | Receive Currency | Mid-Market FX (1 USD →) | NexaRemit FX (1 USD →) | FX Markup % | NexaRemit Fee USD | Recipient Amount | All-in Cost to Sender USD | Margin Check
1 | Nigeria | NGN | 1650 | 1633 | 1.03% | 0 | 163300 | 100 | OK ≥ $0.35
2 | Ghana | GHS | 15.2 | 15.05 | 0.9868% | 0 | 1505 | 100 | OK ≥ $0.35
3 | Kenya | KES | 128.5 | 127.2 | 1.012% | 0 | 12720 | 100 | OK ≥ $0.35
Guardrail: FX markup must cover ≥ $0.35 contribution margin at send=$100 (i.e., FX markup ≥ 0.35%). REVIEW flag means margin fails guardrail.
P1-2 · Mexico (MXN) — Beat Remitly on All-in Cost
Remitly typical fee is $1.99 to Mexico. Target: $0.99 fee + tighter FX. All-in cost must be lower than Remitly's.
# | Provider | Fee USD | Mid-Market FX | Offered FX | FX Markup % | Recipient MXN | All-in Cost USD | Delta vs NexaRemit USD | Verdict
1 | NexaRemit (target) | 0.99 | 18.2 | 18.02 | 0.989% | 1784.1602 | 100.99 | 0 | Baseline
2 | Remitly (published) | 1.99 | 18.2 | 17.82 | 2.088% | 1746.5382 | 101.99 | 1 | NexaRemit wins
3 | Xoom (published) | 0 | 18.2 | 17.65 | 3.022% | 1765 | 100 | -0.99 | Adjust FX
4 | Wise (published) |  | 18.2 | [5 empty] | Capture live quote (see P1-5)
Verdict formula: NexaRemit wins when its all-in cost (H15) is LOWER than the competitor's all-in cost. If not, tighten FX or reduce fee and re-check.
P1-3 · Philippines (PHP) — Beat Xoom on FX Spread
Xoom markets $0 fee on eligible PH transactions but embeds FX spread. Target: $0.99 fee + ≤0.75% FX markup so all-in cost still beats Xoom.
# | Provider | Fee USD | Mid-Market FX | Offered FX | FX Markup % | Recipient PHP | All-in Cost USD | Delta vs NexaRemit USD | Verdict
1 | NexaRemit (target) | 0.99 | 57.8 | 57.37 | 0.7439% | 5680.2037 | 100.99 | 0 | Baseline
2 | Xoom (published) | 0 | 57.8 | 56.4 | 2.422% | 5640 | 100 | -0.99 | NexaRemit wins (more PHP delivered)
3 | Wise (published) |  | 57.8 | [5 empty] | Capture live quote
4 | Remitly (published) |  | 57.8 | [5 empty] | Capture live quote
When fees are both ~$0, the winner is whoever delivers MORE local currency (higher G). Use PHP recipient amount as the tie-breaker.
P1-4 · India (INR) — Attack Xoom's FX Spread
Xoom INR spread cited at 2.5%–4%. UPI/IMPS makes tight FX affordable. Target: $1.49 fee + ≤1.00% FX markup.
# | Provider | Fee USD | Mid-Market FX | Offered FX | FX Markup % | Recipient INR | All-in Cost USD | Effective Cost % of Send | Verdict
1 | NexaRemit (target) | 1.49 | 83.2 | 82.37 | 0.9976% | 8114.2687 | 101.49 | 2.488% | Baseline
2 | Xoom (low estimate) | 0.3 | 83.2 | 81.12 | 2.5% | 8087.664 | 100.3 | 2.8% | NexaRemit wins on all-in %
3 | Xoom (high estimate) | 0.3 | 83.2 | 79.872 | 4% | 7963.2384 | 100.3 | 4.3% | NexaRemit wins on all-in %
4 | Wise (published) |  | 83.2 | [5 empty] | Capture live quote
Effective Cost % = (Fee + FX Markup on $100) / Send. NexaRemit wins when its Effective Cost % is below both Xoom estimates.
P1-5 · Weekly Live Competitor Quote Capture
Weekly ops task: log into each competitor with send=$100 and capture Fee + FX. Paste values in yellow cells. All-in Cost, FX Markup %, and Winner are auto-calculated.
# | Week Of (Mon) | Corridor | Provider | Fee USD | Offered FX (1 USD →) | Mid-Market FX (1 USD →) | FX Markup % | All-in Cost USD (fee + FX cost) | Notes / Source URL
1 | 2026-07-06 | Nigeria | NexaRemit
2 |  | Nigeria | TapTap Send
3 |  | Nigeria | Wise
4 |  | Nigeria | Remitly
5 |  | Nigeria | WorldRemit
6 |  | Nigeria | Xoom
7 |  | Ghana | NexaRemit
8 |  | Ghana | TapTap Send
9 |  | Ghana | Wise
10 |  | Ghana | Remitly
11 |  | Ghana | WorldRemit
12 |  | Ghana | Xoom
13 |  | India | NexaRemit
14 |  | India | TapTap Send
15 |  | India | Wise
16 |  | India | Remitly
17 |  | India | WorldRemit
18 |  | India | Xoom
19 |  | Kenya | NexaRemit
20 |  | Kenya | TapTap Send
21 |  | Kenya | Wise
22 |  | Kenya | Remitly
23 |  | Kenya | WorldRemit
24 |  | Kenya | Xoom
25 |  | Philippines | NexaRemit
26 |  | Philippines | TapTap Send
27 |  | Philippines | Wise
28 |  | Philippines | Remitly
29 |  | Philippines | WorldRemit
30 |  | Philippines | Xoom
31 |  | Mexico | NexaRemit
32 |  | Mexico | TapTap Send
33 |  | Mexico | Wise
34 |  | Mexico | Remitly
35 |  | Mexico | WorldRemit
36 |  | Mexico | Xoom
P1 Rollout Checklist
P1-1 Hero pricing published (NGN, GHS, KES) |  | Target go-live: within 2 weeks. Owner: Growth + Pricing.
P1-2 Mexico $0.99 fee live |  | Target go-live: within 2 weeks. A/B test $0.99 vs $0.00 for 4 weeks.
P1-3 Philippines $0.99 + ≤0.75% FX live |  | Target go-live: within 3 weeks. Add 'You save vs Xoom' widget.
P1-4 India $1.49 + ≤1.00% FX live |  | Target go-live: within 3 weeks. Display mid-market rate on quote screen.
P1-5 Weekly quote capture running |  | Cadence: every Monday. Populate rows 42–77 of this sheet.

## P2 Implementation
P2 Implementation — Calculator Spec · Guardrails · Next Corridor
Operational tables for the 3 P2 recommendations. Yellow-tinted cells are inputs (edit these). White cells with formulas auto-recalculate.
P2-6 · Public 'Total Cost' Calculator — Design Spec + Live Prototype
Prototype the calculator logic here. When implemented on nexaremit.com/pricing it must show fee, FX markup, recipient amount, and savings vs each competitor with no login required.
# | Field / Competitor | Value / Fee USD | Mid-Market FX | Offered FX | FX Markup % | Recipient Local | All-in Cost USD | Savings vs NexaRemit USD | Winner Flag
1 | Send Amount USD | 100
2 | Corridor (label only) | Mexico (MXN)
3 | NexaRemit fee USD | 0.99 | 18.2 | 18.02 | 0.989% | 1784.1602 | 100.99 | 0 | Baseline
4 | Remitly | 1.99 | 18.2 | 17.82 | 2.088% | 1746.5382 | 101.99 | 1 | NexaRemit saves
5 | Xoom | 0 | 18.2 | 17.65 | 3.022% | 1765 | 100 | -0.99 | NexaRemit delivers more MXN
6 | Wise | 6.43 | 18.2 | 18.2 | 0% | 1702.974 | 106.43 | 5.44 | NexaRemit saves
7 | WorldRemit |  | 18.2 | [5 empty] | Capture live quote
8 | TapTap Send | 0 | 18.2 | 17.55 | 3.571% | 1755 | 100 | -0.99 | NexaRemit delivers more MXN
How this becomes production: the calculator page reads Send Amount + Corridor from the user, pulls Mid-Market FX from a public FX API, pulls Offered FX + Fee from NexaRemit's pricing service, and renders the same math shown in rows 9–14 with a live 'You save $X vs [Competitor]' line.
Calculator UX Requirements
# | Requirement | Description |  |  |  | Acceptance Criteria |  | Priority | Owner
1 | No login required | Anonymous visitor can get a full quote |  |  |  | Zero auth prompts before result render |  | Must | Product
2 | Mid-market reference visible | Show mid-market rate next to offered rate |  |  |  | Both rates visible in same viewport |  | Must | Product
3 | Live competitor delta | 'You save $X vs [Remitly/Xoom/Wise]' displayed per corridor |  |  |  | Delta refreshes when user changes amount/corridor |  | Must | Product + Data
4 | Corridor picker | Dropdown of all supported corridors |  |  |  | All 6 corridors + 'Other coming soon' entry |  | Must | Product
5 | Shareable URL | Quote result deep-linkable (query params) |  |  |  | /pricing?send=100&corridor=MXN opens with values pre-filled |  | Should | Engineering
6 | Mobile-first layout | Single column at ≤640px, side-by-side ≥1024px |  |  |  | Lighthouse mobile score ≥ 90 |  | Should | Design + Eng
P2-7 · Guardrails-as-Code — Pricing Service Rules
Enforce these rules automatically in the pricing service. Do not review manually in a spreadsheet. Each rule has a trigger, action, and severity.
# | Rule Name | Trigger Condition | Action | Severity | Alert Channel | Owner | Test Method | Live Status | Notes
1 | Minimum margin | Quote contribution margin < $0.35 | Reject quote; return HTTP 422 | Critical | PagerDuty | Engineering | Unit test: mock quote with margin=$0.30 must throw | Not implemented | Applies to every corridor at send ≥ $50
2 | FX markup cap (Hero) | Offered FX markup > 1.25% on NGN/GHS/KES | Reject quote; auto-page pricing on-call | Critical | PagerDuty | Engineering | Integration test per hero corridor | Not implemented | Hero corridors capped tighter than core
3 | FX markup cap (Core) | Offered FX markup > 1.00% on PHP/MXN/INR | Reject quote; log warn | High | Slack #pricing-alerts | Engineering | Integration test per core corridor | Not implemented | Core corridors get slightly wider band than hero
4 | Hero loss cap | Cumulative Hero corridor loss for month > marketing budget | Auto-flag corridor for review; pause promo FX | High | Slack + email to Growth lead | Growth + Finance | Nightly job compares MTD loss vs budget row | Not implemented | Reset first of each month
5 | Tier-move trigger (to Core) | 3 consecutive months of negative unit margin on any corridor | Auto-flag corridor to move from Hero → Core | Medium | Slack #pricing-alerts | Pricing | Monthly cron job on financial data | Not implemented | Reference: NexaRemit Strategy row 16
6 | Tier-move trigger (to Hero) | Corridor monthly volume > threshold AND competitor headline fee = $0 | Auto-flag corridor to move Core → Hero | Medium | Slack #pricing-alerts | Pricing + Growth | Monthly cron job on volume + competitor scrape | Not implemented | Reference: NexaRemit Strategy row 17
7 | Promo abuse detector | Same user creates > 3 first-transfer promo quotes in 30 days | Block promo FX; charge steady-state rate | High | Slack #fraud-alerts | Risk + Engineering | Weekly sample audit | Not implemented | Prevent Remitly-style promo drain
8 | Competitor fee gap alert | Competitor headline fee drops > $0.50 below NexaRemit for same corridor | Alert pricing lead; propose new fee within 48h | Medium | Email daily digest | Pricing | Uses Weekly Quote Capture from P1-5 | Not implemented | Prevents surprise loss of price leadership
Definition of done for P2-7: every rule row has Live Status = 'Live' with test evidence linked in the Notes column.
P2-8 · Next-Corridor Scorecard — Which Market to Launch
Weighted score across 5 dimensions. Higher = better candidate. Weights sum to 100%. Adjust weights in row 43 (yellow cells) to run sensitivity analysis.
| Dimension → | Diaspora Size (US) | Payout Rail Readiness | Competitive Intensity (inverse) | Regulatory Ease | Avg Send Amount | TOTAL WEIGHT
Weight % |  | 30% | 20% | 20% | 15% | 15% | 100%
Score each candidate 1–10 per dimension in the yellow cells below. Weighted Score = SUMPRODUCT of scores × weights above.
# | Candidate Corridor | Diaspora Size | Payout Rails | Comp. Intensity (inv) | Regulatory Ease | Avg Send | Weighted Score | Rank | Notes
1 | Bangladesh (BDT) | 8 | 7 | 6 | 6 | 7 | 6.95 | 1 | Large diaspora; bKash + Nagad dominant e-wallets; strong incumbent (bKash-Western Union).
2 | Pakistan (PKR) | 8 | 6 | 7 | 5 | 7 | 6.8 | 2 | Sizeable US diaspora; RAAST rail improving; SBP FX rules require care.
3 | Senegal (XOF) | 5 | 8 | 8 | 7 | 6 | 6.65 | 4 | Wave dominant + strong mobile money; less crowded on US-origination.
4 | Dominican Rep. (DOP) | 7 | 8 | 5 | 8 | 6 | 6.8 | 2 | Strong Xoom / Remitly presence; regulatory environment friendly.
5 | (Add candidate) | [5 empty] | 0 | 5 | Yellow cells left blank for future candidate
6 | (Add candidate) | [5 empty] | 0 | 5 | Yellow cells left blank for future candidate
Selected Next Corridor (write once decision is made)
Selected |  | Weighted Score |  | Target Launch Date |  | Owner | Strategy
Once selected, populate rows 47–52 of the Comparison Matrix ('Other' block) with this corridor and begin the same P1 pricing workbench pattern in a new tab.
P2 Rollout Checklist
P2-6 Public calculator live at nexaremit.com/pricing |  | Target: within 4 weeks. Owner: Product + Engineering. Acceptance: all 6 UX Musts satisfied.
P2-7 Guardrails-as-code deployed |  | Target: within 6 weeks. Owner: Engineering. Acceptance: all 8 rules Live Status = 'Live' with tests.
P2-8 Next corridor selected + P1 workbench started |  | Target: within 4 weeks. Owner: Strategy. Acceptance: winner picked in row 54, Comparison Matrix rows 47–52 populated.

## P3 Implementation
P3 Implementation — Legacy Benchmarks · Promo-vs-Steady-State Tracking
Operational tables for the 2 P3 recommendations. Yellow-tinted cells are inputs (edit these). White cells with formulas auto-recalculate.
P3-9 · Legacy Competitor Benchmark — Western Union & MoneyGram
Establish the upper bound on 'expensive'. WU and MoneyGram set the reference incumbents. Use this delta in marketing ('save up to $X vs Western Union').
# | Corridor | Provider | Fee USD | Offered FX (1 USD →) | Mid-Market FX | FX Markup % | All-in Cost USD | Delta vs NexaRemit Target USD | Notes / Source URL
1 | Nigeria (NGN) | Western Union
2 | Nigeria (NGN) | MoneyGram
3 | Ghana (GHS) | Western Union
4 | Ghana (GHS) | MoneyGram
5 | Kenya (KES) | Western Union
6 | Kenya (KES) | MoneyGram
7 | Mexico (MXN) | Western Union
8 | Mexico (MXN) | MoneyGram
9 | Philippines (PHP) | Western Union
10 | Philippines (PHP) | MoneyGram
11 | India (INR) | Western Union
12 | India (INR) | MoneyGram
Delta column shows how much more (positive) or less (negative) the legacy provider costs vs NexaRemit's target all-in cost. Positive = marketing headline ('save $X vs Western Union').
Marketing Headline Auto-Generator
# | Corridor | Best Legacy Reference | Legacy All-in Cost | NexaRemit Target | Savings USD | Savings % | Suggested Headline
1 | Nigeria | Higher of WU/MG | 0 | 100.75 | -100.75 | -100% | Send to Nigeria and save $-100.75 vs Western Union — no transfer fees.
2 | Ghana | Higher of WU/MG | 0 | 100.75 | -100.75 | -100% | Send to Ghana and save $-100.75 vs Western Union — no transfer fees.
3 | Kenya | Higher of WU/MG | 0 | 100.75 | -100.75 | -100% | Send to Kenya and save $-100.75 vs Western Union — no transfer fees.
4 | Mexico | Higher of WU/MG | 0 | 101.49 | -101.49 | -100% | Send to Mexico for $0.99 and save $-101.49 vs Western Union.
5 | Philippines | Higher of WU/MG | 0 | 101.49 | -101.49 | -100% | Send to the Philippines for $0.99 and save $-101.49 vs Western Union.
6 | India | Higher of WU/MG | 0 | 101.99 | -101.99 | -100% | Send to India for $1.49 and save $-101.99 vs Western Union.
P3-10 · Promo vs Steady-State Rate Tracking
Remitly and Xoom offer promotional first-transfer rates that are not sustainable. Separate promo quotes from steady-state so rankings reflect actual repeat-user pricing.
Classification Rules — When to Flag a Quote as 'Promo'
# | Rule | Trigger | Description |  |  | Auto-Flag Value | Applies To | Confidence | Notes
1 | First-transfer marker | Page shows 'special rate on first transfer' | Quote explicitly labeled as new-user promotional rate on landing page or checkout |  |  | Promo | Remitly, Xoom, WorldRemit | High | Most explicit signal
2 | FX better than mid-market | Offered FX ≥ mid-market rate | If Offered FX equals or exceeds the mid-market rate, the provider is subsidizing FX — promo behavior |  |  | Promo | Any provider | High | Sustainable providers always take some FX spread
3 | FX markup < 0.10% | Offered FX markup below 0.10% | Extremely tight FX spread indicates loss-leader promo pricing |  |  | Promo | Any provider | Medium | Wise legitimately runs tight but rarely below 0.10%
4 | Fee = $0 + tight FX | Fee=$0 AND FX markup < 0.50% | Combination of no fee and near-mid-market FX is almost always promotional |  |  | Promo | Any provider | Medium | TapTap steady-state has fee=$0 but wider FX
5 | Repeat capture check | Same corridor/provider quote taken 4 weeks apart differ by > 1.5% | If steady-state price drifts materially week-over-week, prior weeks were promo |  |  | Reclassify prior as Promo | Any provider | Medium | Requires 4+ weeks of Weekly Quote Capture history
6 | Explicit disclaimer | Provider footer states 'promotional', 'introductory', 'limited time' | Language on the quote or checkout screen that explicitly describes the pricing as temporary |  |  | Promo | Any provider | High | Screenshot for evidence
A quote flagged 'Promo' by ANY rule above is excluded from steady-state ranking. Reclassification is manual — apply the rule label in the log below.
Classified Quote Log — Promo vs Steady-State
# | Week Of | Corridor | Provider | Fee USD | FX Markup % | All-in Cost USD | Classification | Rule Applied | Notes / Screenshot URL
1 | 2026-07-06 | Mexico | Remitly | 1.99 | 0.5% | 2.49 | Steady-state | N/A | Second-time user quote — matches published $1.99 baseline
2 | 2026-07-06 | Mexico | Remitly | 1.99 | -1% | 0.99 | Promo | Rule 2 | First-transfer rate — FX better than mid-market
3 | 2026-07-06 | Philippines | Xoom | 0 | 0.2% | 0.2 | Promo | Rule 4 | Fee=$0 AND FX markup < 0.50% → promo
4
5
6
7
8
9
10
11
12
13
Steady-State Cheapest Per Corridor (Promo excluded)
# | Corridor | Cheapest Provider (steady-state) | Min All-in Cost USD | NexaRemit Target | Delta USD | NexaRemit Wins? |  |  | Method
1 | Nigeria |  | 0 | 100.75 | -100.75 | Yes |  |  | MINIFS on Classification=Steady-state
2 | Ghana |  | 0 | 100.75 | -100.75 | Yes |  |  | MINIFS on Classification=Steady-state
3 | Kenya |  | 0 | 100.75 | -100.75 | Yes |  |  | MINIFS on Classification=Steady-state
4 | Mexico | Remitly | 2.49 | 101.49 | -99 | Yes |  |  | MINIFS on Classification=Steady-state
5 | Philippines |  | 0 | 101.49 | -101.49 | Yes |  |  | MINIFS on Classification=Steady-state
6 | India |  | 0 | 101.99 | -101.99 | Yes |  |  | MINIFS on Classification=Steady-state
This block auto-updates as ops classify new rows in the log above. Only rows with Classification='Steady-state' feed the ranking.
P3 Rollout Checklist
P3-9 Legacy competitor quotes captured (WU + MG × 6 corridors) |  | Target: within 4 weeks. Owner: Ops. Acceptance: 12 quote rows populated, headline generator produces text for all 6 corridors.
P3-10 Promo classification live |  | Target: within 6 weeks. Owner: Analytics + Ops. Acceptance: every quote in P1-5 weekly log classified as Promo or Steady-state; steady-state cheapest table populated.